## 0206
Daily Status Report
Project Title: | SIT 1.1 End to End Testing
Current status | SIT Start | SIT End
| 2105-06-02 | 2105-06-05
SIT Execution Status
Service Domain | Total Test Cases | Passed | Failed | Not Completed | Blocked | Not Run | %Complete | % Passed*
CardFacility | 49 | 0 | 0 | 0 | 0 | 49 | 0% | #DIV/0!
ConsumerFinanceDataSync | 12 | 3 | 0 | 0 | 0 | 9 | 25% | 100%
ConsumerFinanceServices | 48 | 15 | 0 | 0 | 0 | 33 | 31.25% | 100%
Correspondence | 13 | 13 | 0 | 0 | 0 | 0 | 100% | 100%
CustomerAccessEntitlement | 9 | 2 | 0 | 0 | 0 | 7 | 22.22% | 100%
CustomerCase | 3 | 0 | 0 | 0 | 0 | 3 | 0% | #DIV/0!
CustomerEventHistory | 6 |  |  |  |  | 6 | 0% | #DIV/0!
DepositAccount | 2 |  |  |  |  | 2 | 0% | #DIV/0!
DocumentServices | 4 |  |  |  |  | 4 | 0% | #DIV/0!
FinancialMessageGateway | 6 |  |  |  |  | 6 | 0% | #DIV/0!
InformationProviderAdmin | 15 |  |  |  |  | 15 | 0% | #DIV/0!
Notifications | 3 |  |  |  |  | 3 | 0% | #DIV/0!
OnboardCustomer | 17 | 3 | 0 | 0 | 0 | 14 | 17.65% | 100%
PartyAuthentication | 20 | 0 | 0 | 0 | 0 | 20 | 0% | #DIV/0!
PartyDataManagement_v1_1 | [5 empty] | 0 | #DIV/0! | #DIV/0!
PartyProfile_v1_0 | [5 empty] | 0 | #DIV/0! | #DIV/0!
PaymentOrder_v1_1 | 28 |  |  |  |  | 28 | 0% | #DIV/0!
PaymentsExecution_v1_1 | 19 |  |  |  |  | 19 | 0% | #DIV/0!
PositionKeeping_v1_1 | 14 |  |  |  |  | 14 | 0% | #DIV/0!
ProspectManagement_v1_1 | 8 | 8 | 0 | 0 | 0 | 0 | 100% | 100%
Reference_Management_Batch | 6 |  |  |  |  | 6 | 0% | #DIV/0!
ReferenceManagement | 2 |  |  |  |  | 2 | 0% | #DIV/0!
ServicingEventHistory_v1_1 | 6 |  |  |  |  | 6 | 0% | #DIV/0!
ServicingIssue_v1_0 | 30 |  |  |  |  | 30 | 0% | #DIV/0!
SystemsOperations_v1_0 | 4 |  |  |  |  | 4 | 0% | #DIV/0!
Batch Testing | [5 empty] | 0 | #DIV/0! | #DIV/0!
Totals | 324 | 44 | 0 | 0 | 0 | 280 | 13.58% | 100%
*Passed % is based on Test Cases in Passed, Failed, or Blocked state only
Comments
Finacle Notifications are not working
Party Data Management and Deposit Account test cases are yet to pull in.
Defect ID | Defect Description |  |  |  |  | Status | Severity | Assigned To
Project State | Green

## 0306
Daily Status Report
Project Title: | SIT 1.1 End to End Testing
Current status | SIT Start | SIT End
| 2105-06-02 | 2105-06-05
SIT Execution Status
Service Domain | Total Test Cases | Passed | Failed | Not Completed | Blocked | Not Run | %Complete | % Passed*
CardFacility | 49 | 9 | 0 | 0 | 0 | 40 | 18.37% | 100%
ConsumerFinanceDataSync | 12 | 9 | 0 | 0 | 0 | 3 | 75% | 100%
ConsumerFinanceServices | 48 | 19 | 0 | 0 | 0 | 29 | 39.58% | 100%
Correspondence | 13 | 13 | 0 | 0 | 0 | 0 | 100% | 100%
CustomerAccessEntitlement | 9 | 2 | 0 | 0 | 0 | 7 | 22.22% | 100%
CustomerCase | 3 | 0 | 0 | 0 | 0 | 3 | 0% | #DIV/0!
CustomerEventHistory | 6 |  |  |  |  | 6 | 0% | #DIV/0!
DepositAccount | 38 |  |  |  |  | 38 | 0% | #DIV/0!
DocumentServices | 4 |  |  |  |  | 4 | 0% | #DIV/0!
FinancialMessageGateway | 6 |  |  |  |  | 6 | 0% | #DIV/0!
InformationProviderAdmin | 15 |  |  |  |  | 15 | 0% | #DIV/0!
Notifications | 3 |  |  |  |  | 3 | 0% | #DIV/0!
OnboardCustomer | 17 | 16 | 0 | 1 | 0 | 0 | 94.12% | 100%
PartyAuthentication | 20 | 0 | 0 | 0 | 0 | 20 | 0% | #DIV/0!
PartyDataManagement_v1_1 | [5 empty] | 0 | #DIV/0! | #DIV/0!
PaymentOrder_v1_1 | 28 |  |  |  |  | 28 | 0% | #DIV/0!
PaymentsExecution_v1_1 | 19 |  |  |  |  | 19 | 0% | #DIV/0!
PositionKeeping_v1_1 | 14 |  |  |  |  | 14 | 0% | #DIV/0!
ProspectManagement_v1_1 | 8 | 8 | 0 | 0 | 0 | 0 | 100% | 100%
Reference_Management_Batch | 6 |  |  |  |  | 6 | 0% | #DIV/0!
ReferenceManagement | 2 |  |  |  |  | 2 | 0% | #DIV/0!
ServicingEventHistory_v1_1 | 6 |  |  |  |  | 6 | 0% | #DIV/0!
ServicingIssue_v1_0 | 30 |  |  |  |  | 30 | 0% | #DIV/0!
SystemsOperations_v1_0 | 4 |  |  |  |  | 4 | 0% | #DIV/0!
Batch Testing | [5 empty] | 0 | #DIV/0! | #DIV/0!
Totals | 360 | 76 | 0 | 1 | 0 | 283 | 21.11% | 100%
*Passed % is based on Test Cases in Passed, Failed, or Blocked state only
Comments
Finacle Notifications are not working - Working fine today
Party Data Management and Deposit Account test cases are yet to pull in - Work in Progress
Defect ID | Defect Description |  |  |  |  | Status | Severity | Assigned To
Project State | Red

## 0406
Daily Status Report
Project Title: | SIT 1.1 End to End Testing
Current status | SIT Start | SIT End
| 2105-06-02 | 2105-06-05
SIT Execution Status
Service Domain | Total Test Cases | Passed | Failed | Not Completed | Blocked | Not Run | %Complete | % Passed*
CardFacility | 53 | 20 | 0 | 0 | 0 | 33 | 37.74% | 100% | Saran
ConsumerFinanceDataSync | 12 | 12 | 0 | 0 | 0 | 0 | 100% | 100%
ConsumerFinanceServices | 48 | 48 | 0 | 0 | 0 | 0 | 100% | 100%
Correspondence | 13 | 13 | 0 | 0 | 0 | 0 | 100% | 100%
CustomerAccessEntitlement | 9 | 9 | 0 | 0 | 0 | 0 | 100% | 100%
CustomerCase | 3 | 0 | 0 | 0 | 0 | 3 | 0% | #DIV/0!
CustomerEventHistory | 6 | 0 | 0 | 0 | 0 | 6 | 0% | #DIV/0!
DepositAccount | 139 | 1 | 0 | 0 | 0 | 138 | 0.7194% | 100%
DocumentServices | 4 | 0 | 0 | 0 | 0 | 4 | 0% | #DIV/0!
FinancialMessageGateway | 6 | 0 | 0 | 0 | 0 | 6 | 0% | #DIV/0!
InformationProviderAdmin | 15 | 7 | 0 | 0 | 0 | 8 | 46.67% | 100%
Notifications | 3 | 0 | 0 | 0 | 0 | 3 | 0% | #DIV/0!
OnboardCustomer | 17 | 16 | 0 | 1 | 0 | 0 | 94.12% | 100%
PartyAuthentication | 20 | 0 | 0 | 0 | 0 | 20 | 0% | #DIV/0!
PartyDataManagement_v1_1 | 209 | 4 | 0 | 0 | 0 | 205 | 1.914% | 100%
PaymentOrder_v1_1 | 47 | 15 | 0 | 0 | 0 | 32 | 31.91% | 100% |  | \
PaymentsExecution_v1_1 | 19 | 0 | 0 | 0 | 0 | 19 | 0% | #DIV/0!
PositionKeeping_v1_1 | 21 | 19 | 0 | 0 | 0 | 2 | 90.48% | 100%
ProspectManagement_v1_1 | 8 | 8 | 0 | 0 | 0 | 0 | 100% | 100%
Reference_Management_Batch | 6 | 0 | 0 | 0 | 0 | 6 | 0% | #DIV/0!
ReferenceManagement | 2 | 0 | 0 | 0 | 0 | 2 | 0% | #DIV/0!
ServicingEventHistory_v1_1 | 6 | 4 | 0 | 0 | 0 | 2 | 66.67% | 100%
ServicingIssue_v1_0 | 30 | 0 | 0 | 0 | 0 | 30 | 0% | #DIV/0!
SystemsOperations_v1_0 | 4 | 0 | 0 | 0 | 0 | 4 | 0% | #DIV/0!
Batch Testing | [5 empty] | 0 | #DIV/0! | #DIV/0!
Totals | 700 | 176 | 0 | 1 | 0 | 523 | 25.14% | 100%
*Passed % is based on Test Cases in Passed, Failed, or Blocked state only
Comments
OnboardParty - SMS notifications are not working
recordPartyeKYC - free cup of Coffee - notifcation still coming even after bio fails
Information Provider Admin - registerPartyRefCode giving 400 error - expecting response back from olive.
Party Data Management test cases are yet to pull in - Completed
Down time of SIT - 1:30 PM to 2:30 PM (3 hours in total)
onboardParty - Notifcaiton issue - Not an Issue
administerPartyAsVerified - issue fixed and closed
Information Provider Admin - recordPartyeKYCDetl - issue fixed and closed
Finacle Notifications are not working - Working fine today
Defect ID | Defect Description |  |  |  |  | Status | Severity | Assigned To
Project State | Red

## 0506
Daily Status Report
Project Title: | SIT 1.1 End to End Testing
Current status | SIT Start | SIT End
| 2015-06-02 | 2015-06-05
Defect ID | Defect Description |  |  |  |  | Status | Severity | Assigned To
2926 | administerDesositNominee - SBAcctMod - Finacle FATAL error |  |  |  |  | Assigned | SL2 | Rox
2928 | onboardParty - SMS notication not coming after onboarding |  |  |  |  | Assigned | SL1 | Rox
2929 | createFDAccount - Error message while creating the FD Account |  |  |  |  | Assigned | SL2 | Rox
2930 | onboardParty - promotion notification still coming up even after bio failed |  |  |  |  | Assigned | SL3 | Rox
SIT Execution Status
Service Domain | Test Cases | Passed | Failed | Not Completed | Blocked | Not Run | %Complete | % Passed*
CardFacility | 53 | 20 | 0 | 0 | 0 | 33 | 37.74% | 100%
ConsumerFinanceDataSync | 12 | 12 | 0 | 0 | 0 | 0 | 100% | 100%
ConsumerFinanceServices | 48 | 48 | 0 | 0 | 0 | 0 | 100% | 100%
Correspondence | 13 | 13 | 0 | 0 | 0 | 0 | 100% | 100%
CustomerAccessEntitlement | 9 | 9 | 0 | 0 | 0 | 0 | 100% | 100%
CustomerCase | 3 | 3 | 0 | 0 | 0 | 0 | 100% | 100%
CustomerEventHistory | 6 | 0 | 0 | 0 | 0 | 6 | 0% | #DIV/0!
DepositAccount | 139 | 18 | 0 | 2 | 0 | 119 | 12.95% | 100%
DocumentServices | 4 | 0 | 0 | 0 | 0 | 4 | 0% | #DIV/0!
FinancialMessageGateway | 6 | 0 | 0 | 0 | 0 | 6 | 0% | #DIV/0!
InformationProviderAdmin | 15 | 7 | 0 | 0 | 0 | 8 | 46.67% | 100%
Notifications | 3 | 0 | 0 | 0 | 0 | 3 | 0% | #DIV/0!
OnboardCustomer | 17 | 16 | 0 | 1 | 0 | 0 | 94.12% | 100%
PartyAuthentication | 20 | 0 | 0 | 0 | 0 | 20 | 0% | #DIV/0!
PartyDataManagement_v1_1 | 209 | 38 | 1 | 0 | 0 | 170 | 18.66% | 97.44%
PaymentOrder_v1_1 | 47 | 43 | 1 | 0 | 0 | 3 | 93.62% | 97.73%
PaymentsExecution_v1_1 | 19 | 0 | 0 | 0 | 0 | 19 | 0% | #DIV/0!
PositionKeeping_v1_1 | 21 | 19 | 0 | 0 | 0 | 2 | 90.48% | 100%
ProspectManagement_v1_1 | 8 | 8 | 0 | 0 | 0 | 0 | 100% | 100%
Reference_Management_Batch | 6 | 0 | 0 | 0 | 0 | 6 | 0% | #DIV/0!
ReferenceManagement | 2 | 0 | 0 | 0 | 0 | 2 | 0% | #DIV/0!
ServicingEventHistory_v1_1 | 6 | 4 | 0 | 0 | 0 | 2 | 66.67% | 100%
ServicingIssue_v1_0 | 30 | 0 | 0 | 0 | 0 | 30 | 0% | #DIV/0!
SystemsOperations_v1_0 | 4 | 0 | 0 | 0 | 0 | 4 | 0% | #DIV/0!
Batch Testing | [5 empty] | 0 | #DIV/0! | #DIV/0!
Totals | 700 | 258 | 2 | 3 | 0 | 437 | 37.14% | 99.23%
*Passed % is based on Test Cases in Passed, Failed, or Blocked state only

## 0606
Daily Status Report
Project Title: | SIT 1.1 End to End Testing
Current status | SIT Start | SIT End
Defect ID | Defect Description |  |  |  |  | Status | Severity | Assigned To
2926 | administerDesositNominee - SBAcctMod - Finacle FATAL error |  |  |  |  | Assigned | SL2 | Hari
2928 | onboardParty - SMS notication not coming after onboarding |  |  |  |  | Assigned | SL1 | Rox
2929 | createFDAccount - Error message while creating the FD Account |  |  |  |  | Assigned | SL2 | Hari
2930 | onboardParty - promotion notification still coming up even after bio failed |  |  |  |  | Assigned | SL3 | Yaseer
2931 | retrievePayeeList: No Record Found - NOT displayed when there are NO FT Payee or Bill Payee |  |  |  |  | SIT Ready | SL3 | Yaseer
2936 | administerPartyAsVerified - Validation error |  |  |  |  | Assigned | SL2 | Rox
SIT Execution Status
Service Domain | Test Cases | Passed | Failed | Not Completed | Blocked | Not Run | %Complete | % Passed*
CardFacility | 53 | 20 | 0 | 0 | 0 | 33 | 37.74% | 100%
ConsumerFinanceDataSync | 12 | 12 | 0 | 0 | 0 | 0 | 100% | 100%
ConsumerFinanceServices | 48 | 48 | 0 | 0 | 0 | 0 | 100% | 100%
Correspondence | 13 | 13 | 0 | 0 | 0 | 0 | 100% | 100%
CustomerAccessEntitlement | 9 | 9 | 0 | 0 | 0 | 0 | 100% | 100%
CustomerCase | 3 | 3 | 0 | 0 | 0 | 0 | 100% | 100%
CustomerEventHistory | 6 | 0 | 0 | 0 | 0 | 6 | 0% | #DIV/0!
DepositAccount | 139 | 75 | 0 | 1 | 0 | 63 | 53.96% | 100%
DocumentServices | 4 | 0 | 0 | 0 | 0 | 4 | 0% | #DIV/0!
FinancialMessageGateway | 6 | 0 | 0 | 0 | 0 | 6 | 0% | #DIV/0!
InformationProviderAdmin | 15 | 7 | 0 | 0 | 0 | 8 | 46.67% | 100%
Notifications | 3 | 0 | 0 | 0 | 0 | 3 | 0% | #DIV/0!
OnboardCustomer | 17 | 16 | 0 | 1 | 0 | 0 | 94.12% | 100%
PartyAuthentication | 20 | 0 | 0 | 0 | 0 | 20 | 0% | #DIV/0!
PartyDataManagement_v1_1 | 209 | 61 | 1 | 0 | 0 | 147 | 29.67% | 98.39%
PaymentOrder_v1_1 | 47 | 43 | 0 | 1 | 0 | 3 | 91.49% | 100%
PaymentsExecution_v1_1 | 19 | 0 | 0 | 0 | 0 | 19 | 0% | #DIV/0!
PositionKeeping_v1_1 | 21 | 19 | 0 | 0 | 0 | 2 | 90.48% | 100%
ProspectManagement_v1_1 | 8 | 8 | 0 | 0 | 0 | 0 | 100% | 100%
Reference_Management_Batch | 6 | 0 | 0 | 0 | 0 | 6 | 0% | #DIV/0!
ReferenceManagement | 2 | 0 | 0 | 0 | 0 | 2 | 0% | #DIV/0!
ServicingEventHistory_v1_1 | 6 | 4 | 0 | 0 | 0 | 2 | 66.67% | 100%
ServicingIssue_v1_0 | 24 | 23 | 1 | 0 | 0 | 0 | 100% | 95.83%
SystemsOperations_v1_0 | 4 | 0 | 0 | 0 | 0 | 4 | 0% | #DIV/0!
Batch Testing | [5 empty] | 0 | #DIV/0! | #DIV/0!
Totals | 694 | 361 | 2 | 3 | 0 | 328 | 52.31% | 99.45%
*Passed % is based on Test Cases in Passed, Failed, or Blocked state only

## 0806
Daily Status Report
Project Title: | SIT 1.1 End to End Testing
Current status | SIT Start | SIT End
Defect ID | Defect Description |  |  |  |  | Status | Severity | Assigned To
2926 | administerDesositNominee - SBAcctMod - Finacle FATAL error |  |  |  |  | Assigned | SL2 | Hari
2928 | onboardParty - SMS notication not coming after onboarding |  |  |  |  | Assigned | SL1 | Rox
2929 | createFDAccount - Error message while creating the FD Account |  |  |  |  | Assigned | SL2 | Hari
2930 | onboardParty - promotion notification still coming up even after bio failed |  |  |  |  | Assigned | SL3 | Yaseer
2931 | retrievePayeeList: No Record Found - NOT displayed when there are NO FT Payee or Bill Payee |  |  |  |  | SIT Ready | SL3 | Yaseer
2936 | administerPartyAsVerified - Validation error |  |  |  |  | Assigned | SL2 | Rox
SIT Execution Status
Service Domain | Test Cases | Passed | Failed | Not Completed | Blocked | Not Run | %Complete | % Passed*
CardFacility | 53 | 20 | 0 | 0 | 0 | 33 | 37.74% | 100%
ConsumerFinanceDataSync | 12 | 12 | 0 | 0 | 0 | 0 | 100% | 100%
ConsumerFinanceServices | 48 | 48 | 0 | 0 | 0 | 0 | 100% | 100%
Correspondence | 13 | 13 | 0 | 0 | 0 | 0 | 100% | 100%
CustomerAccessEntitlement | 9 | 9 | 0 | 0 | 0 | 0 | 100% | 100%
CustomerCase | 3 | 3 | 0 | 0 | 0 | 0 | 100% | 100%
CustomerEventHistory | 6 | 0 | 0 | 0 | 0 | 6 | 0% | #DIV/0!
DepositAccount | 139 | 82 | 0 | 1 | 0 | 56 | 58.99% | 100%
DocumentServices | 4 | 3 | 0 | 0 | 0 | 1 | 75% | 100%
FinancialMessageGateway | 6 | 0 | 0 | 0 | 0 | 6 | 0% | #DIV/0!
InformationProviderAdmin | 15 | 7 | 0 | 0 | 0 | 8 | 46.67% | 100%
Notifications | 3 | 0 | 0 | 0 | 0 | 3 | 0% | #DIV/0!
OnboardCustomer | 17 | 16 | 0 | 1 | 0 | 0 | 94.12% | 100%
PartyAuthentication | 20 | 0 | 0 | 0 | 0 | 20 | 0% | #DIV/0!
PartyDataManagement_v1_1 | 209 | 68 | 1 | 0 | 0 | 140 | 33.01% | 98.55%
PaymentOrder_v1_1 | 47 | 43 | 0 | 1 | 0 | 3 | 91.49% | 100%
PaymentsExecution_v1_1 | 19 | 0 | 0 | 0 | 0 | 19 | 0% | #DIV/0!
PositionKeeping_v1_1 | 21 | 19 | 0 | 0 | 0 | 2 | 90.48% | 100%
ProspectManagement_v1_1 | 8 | 8 | 0 | 0 | 0 | 0 | 100% | 100%
Reference_Management_Batch | 6 | 0 | 0 | 0 | 0 | 6 | 0% | #DIV/0!
ReferenceManagement | 2 | 0 | 0 | 0 | 0 | 2 | 0% | #DIV/0!
ServicingEventHistory_v1_1 | 6 | 4 | 0 | 0 | 0 | 2 | 66.67% | 100%
ServicingIssue_v1_0 | 24 | 24 | 1 | 0 | 0 | -1 | 104.2% | 96%
SystemsOperations_v1_0 | 4 | 0 | 0 | 0 | 0 | 4 | 0% | #DIV/0!
Batch Testing | [5 empty] | 0 | #DIV/0! | #DIV/0!
Totals | 694 | 379 | 2 | 3 | 0 | 310 | 54.9% | 99.48%
*Passed % is based on Test Cases in Passed, Failed, or Blocked state only

## 0906
Daily Status Report
Project Title: | SIT 1.1 End to End Testing
Current status | SIT Start | SIT End
Defect ID | Defect Description |  |  |  |  | Status | Severity | Assigned To
2926 | administerDesositNominee - SBAcctMod - Finacle FATAL error |  |  |  |  | Assigned | SL2-Moderate | roxdsouza
2929 | createFDAccount - Error message while creating the FD Account |  |  |  | gkcharkravarthi | Assigned | SL1-Severe | hsadhu
2931 | retrievePayeeList: No Record Found - NOT displayed when there are NO FT Payee or Bill Payee |  |  |  | gkcharkravarthi | SIT Ready | SL3-Minimal | yaseerrizwan
3034 | createFDAccount - giving the System Database Error |  |  |  | gkcharkravarthi | Assigned | SL2-Moderate | yaseerrizwan
3035 | createFDAccount - error message displayed for duplicate Nickname for another FD Account under the same LCIN |  |  |  | gkcharkravarthi | Assigned | SL2-Moderate | yaseerrizwan
3036 | administerFDNomineeDetails: Error message - A validation occurred while parsing |  |  |  | gkcharkravarthi | Assigned | SL2-Moderate | roxdsouza
3054 | retrieveFDQuote - FD Decimal point issue |  |  |  |  | Assigned | SL2-Moderate | roxdsouza
3120 | administerFutureDatedFundTransfer - Update_Prepone_End_date_series_not_started |  |  |  |  | Assigned | SL2-Moderate | roxdsouza
2928 | onboardParty - SMS notication not coming after onboarding |  |  |  | gkcharkravarthi | Closed | SL2-Moderate | roxdsouza
2930 | onboardParty - promotion notification still coming up even after bio failed |  |  |  | gkcharkravarthi | Closed | SL2-Moderate | yaseerrizwan
2936 | administerPartyAsVerified - Validation error |  |  |  | gkcharkravarthi | Closed | SL2-Moderate | yaseerrizwan
3038 | P2M_Immediate_Mobile_Does_Not_Exists - Defect - executeFinacleScript,SYS,Runtime error has occured |  |  |  |  | Closed | SL2-Moderate | roxdsouza
SIT Execution Status
Service Domain | Test Cases | Passed | Failed | Not Completed | Blocked | Not Run | %Complete | % Passed*
CardFacility | 53 | 26 | 0 | 0 | 0 | 27 | 49.06% | 100%
ConsumerFinanceDataSync | 12 | 12 | 0 | 0 | 0 | 0 | 100% | 100%
ConsumerFinanceServices | 48 | 48 | 0 | 0 | 0 | 0 | 100% | 100%
Correspondence | 13 | 13 | 0 | 0 | 0 | 0 | 100% | 100%
CustomerAccessEntitlement | 9 | 9 | 0 | 0 | 0 | 0 | 100% | 100%
CustomerCase | 3 | 3 | 0 | 0 | 0 | 0 | 100% | 100%
CustomerEventHistory | 6 | 0 | 0 | 0 | 0 | 6 | 0% | 0%
DepositAccount | 139 | 81 | 3 | 1 | 0 | 54 | 60.43% | 96.43%
DocumentServices | 4 | 3 | 0 | 1 | 0 | 0 | 75% | 100%
FinancialMessageGateway | 6 | 6 | 0 | 0 | 0 | 0 | 100% | 100%
InformationProviderAdmin | 15 | 7 | 0 | 0 | 0 | 8 | 46.67% | 100%
Notifications | 3 | 0 | 0 | 0 | 0 | 3 | 0% | 0%
OnboardCustomer | 17 | 16 | 0 | 1 | 0 | 0 | 94.12% | 100%
PartyAuthentication | 20 | 0 | 0 | 0 | 0 | 20 | 0% | 0%
PartyDataManagement_v1_1 | 168 | 76 | 1 | 0 | 0 | 91 | 45.83% | 98.7%
PaymentOrder_v1_1 | 47 | 43 | 0 | 1 | 0 | 3 | 91.49% | 100%
PaymentsExecution_v1_1 | 19 | 13 | 1 | 0 | 0 | 5 | 73.68% | 92.86%
PositionKeeping_v1_1 | 21 | 19 | 0 | 0 | 0 | 2 | 90.48% | 100%
ProspectManagement_v1_1 | 8 | 8 | 0 | 0 | 0 | 0 | 100% | 100%
Reference_Management_Batch | 6 | 0 | 0 | 0 | 0 | 6 | 0% | 0%
ReferenceManagement | 2 | 0 | 0 | 0 | 0 | 2 | 0% | 0%
ServicingEventHistory_v1_1 | 6 | 4 | 0 | 0 | 0 | 2 | 66.67% | 100%
ServicingIssue_v1_0 | 24 | 24 | 1 | 0 | 0 | -1 | 104.2% | 96%
SystemsOperations_v1_0 | 4 | 0 | 0 | 0 | 0 | 4 | 0% | 0%
Batch Testing | [5 empty] | 0 | 0% | 0%
Totals | 653 | 411 | 6 | 4 | 0 | 232 | 63.86% | 98.56%
*Passed % is based on Test Cases in Passed, Failed, or Blocked state only

## 1006
Daily Status Report
Project Title: | SIT 1.1 End to End Testing
Current status | SIT Start | SIT End
Defect ID | Defect Description |  |  |  |  | Status | Severity | Assigned To
2926 | administerDesositNominee - SBAcctMod - Finacle FATAL error |  |  |  |  | Assigned | SL2-Moderate | roxdsouza
2929 | createFDAccount - Error message while creating the FD Account |  |  |  | gkcharkravarthi | Assigned | SL1-Severe | hsadhu
2931 | retrievePayeeList: No Record Found - NOT displayed when there are NO FT Payee or Bill Payee |  |  |  | gkcharkravarthi | SIT Ready | SL3-Minimal | yaseerrizwan
3034 | createFDAccount - giving the System Database Error |  |  |  | gkcharkravarthi | Assigned | SL2-Moderate | yaseerrizwan
3035 | createFDAccount - error message displayed for duplicate Nickname for another FD Account under the same LCIN |  |  |  | gkcharkravarthi | Assigned | SL2-Moderate | yaseerrizwan
3036 | administerFDNomineeDetails: Error message - A validation occurred while parsing |  |  |  | gkcharkravarthi | Assigned | SL2-Moderate | roxdsouza
3054 | retrieveFDQuote - FD Decimal point issue |  |  |  |  | Assigned | SL2-Moderate | roxdsouza
3120 | administerFutureDatedFundTransfer - Update_Prepone_End_date_series_not_started |  |  |  |  | Assigned | SL2-Moderate | roxdsouza
2928 | onboardParty - SMS notication not coming after onboarding |  |  |  | gkcharkravarthi | Closed | SL2-Moderate | roxdsouza
2930 | onboardParty - promotion notification still coming up even after bio failed |  |  |  | gkcharkravarthi | Closed | SL2-Moderate | yaseerrizwan
2936 | administerPartyAsVerified - Validation error |  |  |  | gkcharkravarthi | Closed | SL2-Moderate | yaseerrizwan
3038 | P2M_Immediate_Mobile_Does_Not_Exists - Defect - executeFinacleScript,SYS,Runtime error has occured |  |  |  |  | Closed | SL2-Moderate | roxdsouza
SIT Execution Status
Service Domain | Test Cases | Passed | Failed | Not Completed | Blocked | Not Run | %Complete | % Passed*
CardFacility | 53 | 28 | 0 | 0 | 0 | 25 | 52.83% | 100%
ConsumerFinanceDataSync | 12 | 12 | 0 | 0 | 0 | 0 | 100% | 100%
ConsumerFinanceServices | 48 | 48 | 0 | 0 | 0 | 0 | 100% | 100%
Correspondence | 13 | 13 | 0 | 0 | 0 | 0 | 100% | 100%
CustomerAccessEntitlement | 9 | 9 | 0 | 0 | 0 | 0 | 100% | 100%
CustomerCase | 3 | 3 | 0 | 0 | 0 | 0 | 100% | 100%
CustomerEventHistory | 6 | 0 | 0 | 0 | 0 | 6 | 0% | 0%
DepositAccount | 139 | 83 | 3 | 1 | 0 | 52 | 61.87% | 96.51%
DocumentServices | 4 | 3 | 0 | 1 | 0 | 0 | 75% | 100%
FinancialMessageGateway | 6 | 6 | 0 | 0 | 0 | 0 | 100% | 100%
InformationProviderAdmin | 15 | 7 | 0 | 0 | 0 | 8 | 46.67% | 100%
Notifications | 3 | 0 | 0 | 0 | 0 | 3 | 0% | 0%
OnboardCustomer | 17 | 16 | 0 | 1 | 0 | 0 | 94.12% | 100%
PartyAuthentication | 20 | 4 | 0 | 0 | 0 | 16 | 20% | 0%
PartyDataManagement_v1_1 | 168 | 76 | 1 | 0 | 0 | 91 | 45.83% | 98.7%
PaymentOrder_v1_1 | 47 | 43 | 0 | 1 | 0 | 3 | 91.49% | 100%
PaymentsExecution_v1_1 | 19 | 15 | 1 | 0 | 0 | 3 | 84.21% | 93.75%
PositionKeeping_v1_1 | 21 | 19 | 0 | 0 | 0 | 2 | 90.48% | 100%
ProspectManagement_v1_1 | 8 | 8 | 0 | 0 | 0 | 0 | 100% | 100%
Reference_Management_Batch | 6 | 0 | 0 | 0 | 0 | 6 | 0% | 0%
ReferenceManagement | 2 | 0 | 0 | 0 | 0 | 2 | 0% | 0%
ServicingEventHistory_v1_1 | 6 | 4 | 0 | 0 | 0 | 2 | 66.67% | 100%
ServicingIssue_v1_0 | 24 | 24 | 1 | 0 | 0 | -1 | 104.2% | 96%
SystemsOperations_v1_0 | 4 | 4 | 0 | 0 | 0 | 0 | 100% | 0%
Batch Testing | [5 empty] | 0 | 0% | 0%
Totals | 653 | 425 | 6 | 4 | 0 | 218 | 66% | 98.61%
*Passed % is based on Test Cases in Passed, Failed, or Blocked state only

## 1106
Daily Status Report
Project Title: | SIT 1.1 End to End Testing
Current status | SIT Start | SIT End
Defect ID | Defect Description |  |  |  |  | Status | Severity | Assigned To
2929 | createFDAccount - Error message while creating the FD Account | Assigned | SL1-Severe | roxdsouza |  | Assigned | SL1-Severe | roxdsouza
2931 | retrievePayeeList: No Record Found - NOT displayed when there are NO FT Payee or Bill Payee | Assigned | SL3-Minimal | yaseerrizwan |  | Assigned | SL3-Minimal | yaseerrizwan
3034 | createFDAccount - giving the System Database Error | Assigned | SL2-Moderate | gkcharkravarthi |  | Assigned | SL2-Moderate | gkcharkravarthi
3036 | administerFDNomineeDetails: Error message - A validation occurred while parsing | Assigned | SL2-Moderate | gkcharkravarthi |  | Assigned | SL2-Moderate | gkcharkravarthi
3205 | Update_Postpone_End_date_series_not_started - UPDATE_DATE is null - READ_ONLY Field is null | Assigned | SL2-Moderate | roxdsouza |  | Assigned | SL2-Moderate | roxdsouza
3220 | createFDAccount with nominee as major giving the finacle error message | Assigned | SL2-Moderate | hsadhu |  | Assigned | SL2-Moderate | hsadhu
3260 | requestCardActivation _DB_Verify_OverseasActivation_InvalidCardNumber_N - Error code is nor correct | Assigned | SL2-Moderate | roxdsouza |  | Assigned | SL2-Moderate | roxdsouza
3276 | CustomerEventHistory_v1_0 - notifyEvent - notifyAction "LoginFailed" - does not creates record in Event_Details table | Assigned | SL2-Moderate | roxdsouza |  | Assigned | SL2-Moderate | roxdsouza
3035 | createFDAccount - error message displayed for duplicate Nickname for another FD Account under the same LCIN | SIT Ready | SL2-Moderate | gkcharkravarthi |  | SIT Ready | SL2-Moderate | gkcharkravarthi
3054 | retrieveFDQuote - FD Decimal point issue | SIT Ready | SL2-Moderate | gkcharkravarthi |  | SIT Ready | SL2-Moderate | gkcharkravarthi
2926 | administerDesositNominee - SBAcctMod - Finacle FATAL error | Closed | SL2-Moderate | roxdsouza | Closed | Closed | SL2-Moderate | roxdsouza
2928 | onboardParty - SMS notication not coming after onboarding | Closed | SL2-Moderate | roxdsouza |  | Closed | SL2-Moderate | roxdsouza
2930 | onboardParty - promotion notification still coming up even after bio failed | Closed | SL2-Moderate | gkcharkravarthi |  | Closed | SL2-Moderate | gkcharkravarthi
2936 | administerPartyAsVerified - Validation error | Closed | SL2-Moderate | roxdsouza |  | Closed | SL2-Moderate | roxdsouza
3038 | P2M_Immediate_Mobile_Does_Not_Exists - Defect - executeFinacleScript,SYS,Runtime error has occured | Closed | SL2-Moderate | gkcharkravarthi |  | Closed | SL2-Moderate | gkcharkravarthi
3120 | administerFutureDatedFundTransfer - Update_Prepone_End_date_series_not_started | Closed | SL1-Severe | gkcharkravarthi |  | Closed | SL1-Severe | gkcharkravarthi
3203 | administerFutureDatedFundTransfer - RecurrCount_Increase | Assigned | SL2-Moderate | roxdsouza |  | Closed | SL2-Moderate | roxdsouza
3204 | administerFutureDatedFundTransfer - Update_Start_date_series_started - The record is modified and is getting cancelled/ DELETED. | Closed | SL1-Severe | gkcharkravarthi |  | Closed | SL1-Severe | gkcharkravarthi
3227 | retriveFDQuote - giving the error message | Closed | SL2-Moderate | gkcharkravarthi |  | Closed | SL2-Moderate | gkcharkravarthi
3259 | requestCardActivation - OverseasActivation/Deactivation | Closed | SL2-Moderate | gkcharkravarthi |  | Closed | SL2-Moderate | gkcharkravarthi
SIT Execution Status
Service Domain | Test Cases | Passed | Failed | Not Completed | Blocked | Not Run | %Complete | % Passed*
CardFacility | 53 | 43 | 1 | 0 | 0 | 9 | 83.02% | 97.73%
ConsumerFinanceDataSync | 12 | 12 | 0 | 0 | 0 | 0 | 100% | 100%
ConsumerFinanceServices | 48 | 48 | 0 | 0 | 0 | 0 | 100% | 100%
Correspondence | 13 | 13 | 0 | 0 | 0 | 0 | 100% | 100%
CustomerAccessEntitlement | 9 | 9 | 0 | 0 | 0 | 0 | 100% | 100%
CustomerCase | 3 | 3 | 0 | 0 | 0 | 0 | 100% | 100%
CustomerEventHistory | 6 | 4 | 1 | 0 | 0 | 1 | 83.33% | 80%
DepositAccount | 138 | 87 | 4 | 2 | 0 | 45 | 65.94% | 95.6%
DocumentServices | 4 | 3 | 0 | 1 | 0 | 0 | 75% | 100%
FinancialMessageGateway | 6 | 6 | 0 | 0 | 0 | 0 | 100% | 100%
InformationProviderAdmin | 15 | 9 | 0 | 0 | 0 | 6 | 60% | 100%
Notifications | 3 | 0 | 0 | 0 | 0 | 3 | 0% | 0%
OnboardCustomer | 17 | 16 | 0 | 1 | 0 | 0 | 94.12% | 100%
PartyAuthentication | 20 | 20 | 0 | 0 | 0 | 0 | 100% | 100%
PartyDataManagement_v1_1 | 130 | 84 | 1 | 0 | 0 | 45 | 65.38% | 98.82%
PaymentOrder_v1_1 | 47 | 45 | 0 | 1 | 0 | 1 | 95.74% | 100%
PaymentsExecution_v1_1 | 19 | 17 | 2 | 0 | 0 | 0 | 100% | 89.47%
PositionKeeping_v1_1 | 21 | 21 | 0 | 0 | 0 | 0 | 100% | 100%
ProspectManagement_v1_1 | 8 | 8 | 0 | 0 | 0 | 0 | 100% | 100%
Reference_Management_Batch | 6 | 0 | 0 | 0 | 0 | 6 | 0% | 0%
ReferenceManagement | 2 | 2 | 0 | 0 | 0 | 0 | 100% | 100%
ServicingEventHistory_v1_1 | 6 | 4 | 0 | 0 | 0 | 2 | 66.67% | 100%
ServicingIssue_v1_0 | 24 | 24 | 0 | 0 | 0 | 0 | 100% | 100%
SystemsOperations_v1_0 | 4 | 4 | 0 | 0 | 0 | 0 | 100% | 100%
Batch Testing | [5 empty] | 0 | 0% | 0%
Totals | 614 | 482 | 9 | 5 | 0 | 118 | 79.97% | 98.17%
*Passed % is based on Test Cases in Passed, Failed, or Blocked state only

## 1606
Daily Status Report
Project Title: | SIT 1.1 End to End Testing
Current status | SIT Start | SIT End
Defect ID | Defect Description |  |  |  |  | Status | Severity | Assigned To
2929 | createFDAccount - Error message while creating the FD Account | Assigned | SL1-Severe | roxdsouza |  | Assigned | SL1-Severe | roxdsouza
2931 | retrievePayeeList: No Record Found - NOT displayed when there are NO FT Payee or Bill Payee | Assigned | SL3-Minimal | yaseerrizwan |  | Assigned | SL3-Minimal | yaseerrizwan
3034 | createFDAccount - giving the System Database Error | Assigned | SL2-Moderate | gkcharkravarthi |  | Assigned | SL2-Moderate | gkcharkravarthi
3036 | administerFDNomineeDetails: Error message - A validation occurred while parsing | Assigned | SL2-Moderate | gkcharkravarthi |  | Assigned | SL2-Moderate | gkcharkravarthi
3205 | Update_Postpone_End_date_series_not_started - UPDATE_DATE is null - READ_ONLY Field is null | Assigned | SL2-Moderate | roxdsouza |  | Assigned | SL2-Moderate | roxdsouza
3220 | createFDAccount with nominee as major giving the finacle error message | Assigned | SL2-Moderate | hsadhu |  | Assigned | SL2-Moderate | hsadhu
3260 | requestCardActivation _DB_Verify_OverseasActivation_InvalidCardNumber_N - Error code is nor correct | Assigned | SL2-Moderate | roxdsouza |  | Assigned | SL2-Moderate | roxdsouza
3276 | CustomerEventHistory_v1_0 - notifyEvent - notifyAction "LoginFailed" - does not creates record in Event_Details table | Assigned | SL2-Moderate | roxdsouza |  | Assigned | SL2-Moderate | roxdsouza
3035 | createFDAccount - error message displayed for duplicate Nickname for another FD Account under the same LCIN | SIT Ready | SL2-Moderate | gkcharkravarthi |  | SIT Ready | SL2-Moderate | gkcharkravarthi
3054 | retrieveFDQuote - FD Decimal point issue | SIT Ready | SL2-Moderate | gkcharkravarthi |  | SIT Ready | SL2-Moderate | gkcharkravarthi
2926 | administerDesositNominee - SBAcctMod - Finacle FATAL error | Closed | SL2-Moderate | roxdsouza | Closed | Closed | SL2-Moderate | roxdsouza
2928 | onboardParty - SMS notication not coming after onboarding | Closed | SL2-Moderate | roxdsouza |  | Closed | SL2-Moderate | roxdsouza
2930 | onboardParty - promotion notification still coming up even after bio failed | Closed | SL2-Moderate | gkcharkravarthi |  | Closed | SL2-Moderate | gkcharkravarthi
2936 | administerPartyAsVerified - Validation error | Closed | SL2-Moderate | roxdsouza |  | Closed | SL2-Moderate | roxdsouza
3038 | P2M_Immediate_Mobile_Does_Not_Exists - Defect - executeFinacleScript,SYS,Runtime error has occured | Closed | SL2-Moderate | gkcharkravarthi |  | Closed | SL2-Moderate | gkcharkravarthi
3120 | administerFutureDatedFundTransfer - Update_Prepone_End_date_series_not_started | Closed | SL1-Severe | gkcharkravarthi |  | Closed | SL1-Severe | gkcharkravarthi
3203 | administerFutureDatedFundTransfer - RecurrCount_Increase | Assigned | SL2-Moderate | roxdsouza |  | Closed | SL2-Moderate | roxdsouza
3204 | administerFutureDatedFundTransfer - Update_Start_date_series_started - The record is modified and is getting cancelled/ DELETED. | Closed | SL1-Severe | gkcharkravarthi |  | Closed | SL1-Severe | gkcharkravarthi
3227 | retriveFDQuote - giving the error message | Closed | SL2-Moderate | gkcharkravarthi |  | Closed | SL2-Moderate | gkcharkravarthi
3259 | requestCardActivation - OverseasActivation/Deactivation | Closed | SL2-Moderate | gkcharkravarthi |  | Closed | SL2-Moderate | gkcharkravarthi
SIT Execution Status
Service Domain | Test Cases | Passed | Failed | Not Completed | Blocked | Not Run | %Complete | % Passed*
CardFacility | 53 | 48 | 1 | 0 | 0 | 4 | 92.45% | 97.96%
ConsumerFinanceDataSync | 12 | 12 | 0 | 0 | 0 | 0 | 100% | 100%
ConsumerFinanceServices | 48 | 48 | 0 | 0 | 0 | 0 | 100% | 100%
Correspondence | 13 | 13 | 0 | 0 | 0 | 0 | 100% | 100%
CustomerAccessEntitlement | 9 | 9 | 0 | 0 | 0 | 0 | 100% | 100%
CustomerCase | 3 | 3 | 0 | 0 | 0 | 0 | 100% | 100%
CustomerEventHistory | 6 | 6 | 0 | 0 | 0 | 0 | 100% | 100%
DepositAccount | 138 | 90 | 4 | 1 | 0 | 43 | 68.12% | 95.74%
DocumentServices | 4 | 3 | 0 | 1 | 0 | 0 | 75% | 100%
FinancialMessageGateway | 6 | 6 | 0 | 0 | 0 | 0 | 100% | 100%
InformationProviderAdmin | 15 | 9 | 0 | 0 | 0 | 6 | 60% | 100%
Notifications | 3 | 0 | 0 | 0 | 0 | 3 | 0% | 0%
OnboardCustomer | 17 | 16 | 0 | 1 | 0 | 0 | 94.12% | 100%
PartyAuthentication | 20 | 20 | 0 | 0 | 0 | 0 | 100% | 100%
PartyDataManagement_v1_1 | 130 | 84 | 1 | 0 | 0 | 45 | 65.38% | 98.82%
PaymentOrder_v1_1 | 47 | 45 | 0 | 1 | 0 | 1 | 95.74% | 100%
PaymentsExecution_v1_1 | 19 | 17 | 2 | 0 | 0 | 0 | 100% | 89.47%
PositionKeeping_v1_1 | 21 | 21 | 0 | 0 | 0 | 0 | 100% | 100%
ProspectManagement_v1_1 | 8 | 8 | 0 | 0 | 0 | 0 | 100% | 100%
Reference_Management_Batch | 6 | 0 | 0 | 0 | 0 | 6 | 0% | 0%
ReferenceManagement | 2 | 2 | 0 | 0 | 0 | 0 | 100% | 100%
ServicingEventHistory_v1_1 | 6 | 4 | 0 | 0 | 0 | 2 | 66.67% | 100%
ServicingIssue_v1_0 | 24 | 24 | 0 | 0 | 0 | 0 | 100% | 100%
SystemsOperations_v1_0 | 4 | 4 | 0 | 0 | 0 | 0 | 100% | 100%
Batch Testing | [5 empty] | 0 | 0% | 0%
Totals | 614 | 492 | 8 | 4 | 0 | 110 | 81.43% | 98.4%
*Passed % is based on Test Cases in Passed, Failed, or Blocked state only

## 1706
Daily Status Report
Project Title: | SIT 1.1 End to End Testing
Current status | SIT Start | SIT End
Defect ID | Defect Description |  |  |  |  | Status | Severity | Assigned To
3510 | DepositeAccount - RetrieveFDTransactionHistory - throwing error when date filters are removed |  |  |  |  | Assigned | SL2-Moderate | roxdsouza
3574 | terminateFDAccount - Error when trying to terminate with out fpmprecloseflage |  |  |  |  | Assigned | SL2-Moderate | roxdsouza
3575 | evaluateDepositAccountClosureEligibility - Error when trying to call this service when the user is having both the Savings and FD Account |  |  |  |  | Assigned | SL2-Moderate | roxdsouza
SIT Execution Status
Service Domain | Test Cases | Passed | Failed | Not Completed | Blocked | Not Run | %Complete | % Passed*
CardFacility | 52 | 52 | 0 | 0 | 0 | 0 | 100% | 100%
ConsumerFinanceDataSync | 12 | 12 | 0 | 0 | 0 | 0 | 100% | 100%
ConsumerFinanceServices | 48 | 48 | 0 | 0 | 0 | 0 | 100% | 100%
Correspondence | 13 | 13 | 0 | 0 | 0 | 0 | 100% | 100%
CustomerAccessEntitlement | 9 | 9 | 0 | 0 | 0 | 0 | 100% | 100%
CustomerCase | 3 | 3 | 0 | 0 | 0 | 0 | 100% | 100%
CustomerEventHistory | 6 | 6 | 0 | 0 | 0 | 0 | 100% | 100%
DepositAccount | 131 | 119 | 3 | 9 | 0 | 0 | 93.13% | 97.54%
DocumentServices | 4 | 3 | 0 | 1 | 0 | 0 | 75% | 100%
FinancialMessageGateway | 6 | 6 | 0 | 0 | 0 | 0 | 100% | 100%
InformationProviderAdmin | 14 | 14 | 0 | 0 | 0 | 0 | 100% | 100%
OnboardCustomer | 17 | 16 | 0 | 1 | 0 | 0 | 94.12% | 100%
PartyAuthentication | 20 | 20 | 0 | 0 | 0 | 0 | 100% | 100%
PartyDataManagement_v1_1 | 114 | 113 | 1 | 0 | 0 | 0 | 100% | 99.12%
PaymentOrder_v1_1 | 44 | 44 | 0 | 0 | 0 | 0 | 100% | 100%
PaymentsExecution_v1_1 | 19 | 17 | 2 | 0 | 0 | 0 | 100% | 89.47%
PositionKeeping_v1_1 | 21 | 21 | 0 | 0 | 0 | 0 | 100% | 100%
ProspectManagement_v1_1 | 8 | 8 | 0 | 0 | 0 | 0 | 100% | 100%
ReferenceManagement | 2 | 2 | 0 | 0 | 0 | 0 | 100% | 100%
ServicingEventHistory_v1_1 | 6 | 4 | 0 | 0 | 0 | 2 | 66.67% | 100%
ServicingIssue_v1_0 | 24 | 24 | 0 | 0 | 0 | 0 | 100% | 100%
SystemsOperations_v1_0 | 4 | 4 | 0 | 0 | 0 | 0 | 100% | 100%
Batch Testing | [5 empty] | 0 | 0% | 0%
Totals | 577 | 558 | 6 | 11 | 0 | 2 | 97.75% | 98.94%
*Passed % is based on Test Cases in Passed, Failed, or Blocked state only

## 1806
Daily Status Report
Project Title: | SIT 1.1 End to End Testing
Current status | SIT Start | SIT End
Defect ID | Defect Description |  |  |  |  | Status | Severity | Assigned To
3574 | terminateFDAccount - Error when trying to terminate with out fpmprecloseflage |  |  |  |  | SIT Ready | SL2-Moderate | gkcharkravarthi
3575 | evaluateDepositAccountClosureEligibility - Error when trying to call this service when the user is having both the Savings and FD Account |  |  |  |  | Assigned | SL2-Moderate | roxdsouza
3672 | terminateFDAccount - error message Profit and Loss A/c [DBRDQCINTE] does not exist with Sol [827] |  |  |  |  | Assigned | SL2-Moderate | roxdsouza
SIT Execution Status
Service Domain | Test Cases | Passed | Failed | Not Completed | Blocked | Not Run | %Complete | % Passed*
CardFacility | 52 | 52 | 0 | 0 | 0 | 0 | 100% | 100%
ConsumerFinanceDataSync | 12 | 12 | 0 | 0 | 0 | 0 | 100% | 100%
ConsumerFinanceServices | 48 | 48 | 0 | 0 | 0 | 0 | 100% | 100%
Correspondence | 13 | 13 | 0 | 0 | 0 | 0 | 100% | 100%
CustomerAccessEntitlement | 9 | 9 | 0 | 0 | 0 | 0 | 100% | 100%
CustomerCase | 3 | 3 | 0 | 0 | 0 | 0 | 100% | 100%
CustomerEventHistory | 6 | 6 | 0 | 0 | 0 | 0 | 100% | 100%
DepositAccount | 131 | 123 | 3 | 5 | 0 | 0 | 96.18% | 93.89%
DocumentServices | 4 | 3 | 0 | 1 | 0 | 0 | 75% | 100%
FinancialMessageGateway | 6 | 6 | 0 | 0 | 0 | 0 | 100% | 100%
InformationProviderAdmin | 14 | 14 | 0 | 0 | 0 | 0 | 100% | 100%
OnboardCustomer | 17 | 16 | 0 | 1 | 0 | 0 | 94.12% | 100%
PartyAuthentication | 20 | 20 | 0 | 0 | 0 | 0 | 100% | 100%
PartyDataManagement_v1_1 | 114 | 113 | 1 | 0 | 0 | 0 | 100% | 99.12%
PaymentOrder_v1_1 | 44 | 44 | 0 | 0 | 0 | 0 | 100% | 100%
PaymentsExecution_v1_1 | 19 | 17 | 2 | 0 | 0 | 0 | 100% | 89.47%
PositionKeeping_v1_1 | 21 | 21 | 0 | 0 | 0 | 0 | 100% | 100%
ProspectManagement_v1_1 | 8 | 8 | 0 | 0 | 0 | 0 | 100% | 100%
ReferenceManagement | 2 | 2 | 0 | 0 | 0 | 0 | 100% | 100%
ServicingEventHistory_v1_1 | 6 | 4 | 0 | 2 | 0 | 0 | 66.67% | 100%
ServicingIssue_v1_0 | 24 | 24 | 0 | 0 | 0 | 0 | 100% | 100%
SystemsOperations_v1_0 | 4 | 4 | 0 | 0 | 0 | 0 | 100% | 100%
Batch Testing | [5 empty] | 0 | 0% | 0%
Totals | 577 | 562 | 6 | 9 | 0 | 0 | 98.44% | 98.94%
*Passed % is based on Test Cases in Passed, Failed, or Blocked state only

## 2306
Daily Status Report
Project Title: | SIT 1.1 End to End Testing
Current status | SIT Start | SIT End
Defect ID | Defect Description |  |  |  |  | Status | Severity | Assigned To
3574 | terminateFDAccount - Error when trying to terminate with out fpmprecloseflage |  |  |  |  | SIT Ready | SL2-Moderate | gkcharkravarthi
3575 | evaluateDepositAccountClosureEligibility - Error when trying to call this service when the user is having both the Savings and FD Account |  |  |  |  | Assigned | SL2-Moderate | roxdsouza
3672 | terminateFDAccount - error message Profit and Loss A/c [DBRDQCINTE] does not exist with Sol [827] |  |  |  |  | Assigned | SL2-Moderate | roxdsouza
SIT Execution Status
Service Domain | Test Cases | Passed | Failed | Not Completed | Blocked | Not Run | %Complete | % Passed*
CardFacility | 52 | 52 | 0 | 0 | 0 | 0 | 100% | 100%
ConsumerFinanceDataSync | 12 | 12 | 0 | 0 | 0 | 0 | 100% | 100%
ConsumerFinanceServices | 48 | 48 | 0 | 0 | 0 | 0 | 100% | 100%
Correspondence | 13 | 13 | 0 | 0 | 0 | 0 | 100% | 100%
CustomerAccessEntitlement | 9 | 9 | 0 | 0 | 0 | 0 | 100% | 100%
CustomerCase | 3 | 3 | 0 | 0 | 0 | 0 | 100% | 100%
CustomerEventHistory | 6 | 6 | 0 | 0 | 0 | 0 | 100% | 100%
DepositAccount | 131 | 123 | 3 | 5 | 0 | 0 | 96.18% | 93.89%
DocumentServices | 4 | 3 | 0 | 1 | 0 | 0 | 75% | 100%
FinancialMessageGateway | 6 | 6 | 0 | 0 | 0 | 0 | 100% | 100%
InformationProviderAdmin | 14 | 14 | 0 | 0 | 0 | 0 | 100% | 100%
OnboardCustomer | 17 | 16 | 0 | 1 | 0 | 0 | 94.12% | 100%
PartyAuthentication | 20 | 20 | 0 | 0 | 0 | 0 | 100% | 100%
PartyDataManagement_v1_1 | 114 | 113 | 1 | 0 | 0 | 0 | 100% | 99.12%
PaymentOrder_v1_1 | 44 | 44 | 0 | 0 | 0 | 0 | 100% | 100%
PaymentsExecution_v1_1 | 19 | 17 | 2 | 0 | 0 | 0 | 100% | 89.47%
PositionKeeping_v1_1 | 21 | 21 | 0 | 0 | 0 | 0 | 100% | 100%
ProspectManagement_v1_1 | 8 | 8 | 0 | 0 | 0 | 0 | 100% | 100%
ReferenceManagement | 2 | 2 | 0 | 0 | 0 | 0 | 100% | 100%
ServicingEventHistory_v1_1 | 6 | 4 | 0 | 2 | 0 | 0 | 66.67% | 100%
ServicingIssue_v1_0 | 24 | 24 | 0 | 0 | 0 | 0 | 100% | 100%
SystemsOperations_v1_0 | 4 | 4 | 0 | 0 | 0 | 0 | 100% | 100%
Batch Testing | [5 empty] | 0 | 0% | 0%
Totals | 577 | 562 | 6 | 9 | 0 | 0 | 98.44% | 98.94%
*Passed % is based on Test Cases in Passed, Failed, or Blocked state only

## 2406
Daily Status Report
Project Title: | SIT 1.1 End to End Testing
Current status | SIT Start | SIT End
Defect ID | Defect Description |  |  |  |  | Status | Severity | Assigned To
3574 | terminateFDAccount - Error when trying to terminate with out fpmprecloseflage |  |  |  |  | Assigned | SL2-Moderate | Hari
3672 | terminateFDAccount - error message Profit and Loss A/c [DBRDQCINTE] does not exist with Sol [827] |  |  |  |  | Assigned | SL2-Moderate | Hari
SIT Execution Status
Service Domain | Test Cases | Passed | Failed | Not Completed | Blocked | Not Run | %Complete | % Passed*
CardFacility | 52 | 52 | 0 | 0 | 0 | 0 | 100% | 100%
ConsumerFinanceDataSync | 12 | 12 | 0 | 0 | 0 | 0 | 100% | 100%
ConsumerFinanceServices | 48 | 48 | 0 | 0 | 0 | 0 | 100% | 100%
Correspondence | 13 | 13 | 0 | 0 | 0 | 0 | 100% | 100%
CustomerAccessEntitlement | 9 | 9 | 0 | 0 | 0 | 0 | 100% | 100%
CustomerCase | 3 | 3 | 0 | 0 | 0 | 0 | 100% | 100%
CustomerEventHistory | 6 | 6 | 0 | 0 | 0 | 0 | 100% | 100%
DepositAccount | 131 | 130 | 1 | 0 | 0 | 0 | 100% | 99.24%
DocumentServices | 4 | 4 | 0 | 0 | 0 | 0 | 100% | 100%
FinancialMessageGateway | 6 | 6 | 0 | 0 | 0 | 0 | 100% | 100%
InformationProviderAdmin | 14 | 14 | 0 | 0 | 0 | 0 | 100% | 100%
OnboardCustomer | 16 | 16 | 0 | 0 | 0 | 0 | 100% | 100%
PartyAuthentication | 20 | 20 | 0 | 0 | 0 | 0 | 100% | 100%
PartyDataManagement_v1_1 | 114 | 114 | 0 | 0 | 0 | 0 | 100% | 100%
PaymentOrder_v1_1 | 48 | 48 | 0 | 0 | 0 | 0 | 100% | 100%
PaymentsExecution_v1_1 | 19 | 19 | 0 | 0 | 0 | 0 | 100% | 100%
PositionKeeping_v1_1 | 21 | 21 | 0 | 0 | 0 | 0 | 100% | 100%
ProspectManagement_v1_1 | 8 | 8 | 0 | 0 | 0 | 0 | 100% | 100%
ReferenceManagement | 2 | 2 | 0 | 0 | 0 | 0 | 100% | 100%
ServicingEventHistory_v1_1 | 4 | 4 | 0 | 0 | 0 | 0 | 100% | 100%
ServicingIssue_v1_0 | 24 | 24 | 0 | 0 | 0 | 0 | 100% | 100%
SystemsOperations_v1_0 | 4 | 4 | 0 | 0 | 0 | 0 | 100% | 100%
Batch Testing | [5 empty] | 0 | 0% | 0%
Totals | 578 | 577 | 1 | 0 | 0 | 0 | 100% | 99%
*Passed % is based on Test Cases in Passed, Failed, or Blocked state only

## 2506
Daily Status Report
Project Title: | SIT 1.1 End to End Testing
Current status | SIT Start | SIT End
SIT Execution Status
Service Domain | Test Cases | Passed | Failed | Not Completed | Blocked | Not Run | %Complete | % Passed*
CardFacility | 52 | 52 | 0 | 0 | 0 | 0 | 100% | 100%
ConsumerFinanceDataSync | 12 | 12 | 0 | 0 | 0 | 0 | 100% | 100%
ConsumerFinanceServices | 48 | 48 | 0 | 0 | 0 | 0 | 100% | 100%
Correspondence | 13 | 13 | 0 | 0 | 0 | 0 | 100% | 100%
CustomerAccessEntitlement | 9 | 9 | 0 | 0 | 0 | 0 | 100% | 100%
CustomerCase | 3 | 3 | 0 | 0 | 0 | 0 | 100% | 100%
CustomerEventHistory | 6 | 6 | 0 | 0 | 0 | 0 | 100% | 100%
DepositAccount | 131 | 131 | 0 | 0 | 0 | 0 | 100% | 100%
DocumentServices | 4 | 4 | 0 | 0 | 0 | 0 | 100% | 100%
FinancialMessageGateway | 6 | 6 | 0 | 0 | 0 | 0 | 100% | 100%
InformationProviderAdmin | 14 | 14 | 0 | 0 | 0 | 0 | 100% | 100%
OnboardCustomer | 16 | 16 | 0 | 0 | 0 | 0 | 100% | 100%
PartyAuthentication | 20 | 20 | 0 | 0 | 0 | 0 | 100% | 100%
PartyDataManagement_v1_1 | 114 | 114 | 0 | 0 | 0 | 0 | 100% | 100%
PaymentOrder_v1_1 | 48 | 48 | 0 | 0 | 0 | 0 | 100% | 100%
PaymentsExecution_v1_1 | 19 | 19 | 0 | 0 | 0 | 0 | 100% | 100%
PositionKeeping_v1_1 | 21 | 21 | 0 | 0 | 0 | 0 | 100% | 100%
ProspectManagement_v1_1 | 8 | 8 | 0 | 0 | 0 | 0 | 100% | 100%
ReferenceManagement | 2 | 2 | 0 | 0 | 0 | 0 | 100% | 100%
ServicingEventHistory_v1_1 | 4 | 4 | 0 | 0 | 0 | 0 | 100% | 100%
ServicingIssue_v1_0 | 24 | 24 | 0 | 0 | 0 | 0 | 100% | 100%
SystemsOperations_v1_0 | 4 | 4 | 0 | 0 | 0 | 0 | 100% | 100%
Batch Testing | [5 empty] | 0 | 0% | 0%
Totals | 578 | 578 | 0 | 0 | 0 | 0 | 100% | 100%
*Passed % is based on Test Cases in Passed, Failed, or Blocked state only

## Defects
Defect ID | Summary | Detected By | Status | Severity | Assigned To | Detected on Date | System
2926 | administerDesositNominee - SBAcctMod - Finacle FATAL error | gkcharkravarthi | Closed | SL2-Moderate | roxdsouza | 2015-06-05 | IP
2928 | onboardParty - SMS notication not coming after onboarding | gkcharkravarthi | Closed | SL2-Moderate | roxdsouza | 2015-06-05 | IP
2930 | onboardParty - promotion notification still coming up even after bio failed | gkcharkravarthi | Closed | SL2-Moderate | gkcharkravarthi | 2015-06-05 | IP
2931 | retrievePayeeList: No Record Found - NOT displayed when there are NO FT Payee or Bill Payee | gkcharkravarthi | Closed | SL3-Minimal | gkcharkravarthi | 2015-06-05 | IP
2936 | administerPartyAsVerified - Validation error | gkcharkravarthi | Closed | SL2-Moderate | roxdsouza | 2015-06-06 | IP
3034 | createFDAccount - giving the System Database Error | gkcharkravarthi | Closed | SL2-Moderate | gkcharkravarthi | 2015-06-09 | IP
3035 | createFDAccount - error message displayed for duplicate Nickname for another FD Account under the same LCIN | gkcharkravarthi | Closed | SL2-Moderate | gkcharkravarthi | 2015-06-09 | IP
3036 | administerFDNomineeDetails: Error message - A validation occurred while parsing | gkcharkravarthi | Closed | SL2-Moderate | gkcharkravarthi | 2015-06-09 | IP
3038 | P2M_Immediate_Mobile_Does_Not_Exists - Defect - executeFinacleScript,SYS,Runtime error has occured | gkcharkravarthi | Closed | SL2-Moderate | gkcharkravarthi | 2015-06-09 | IP
3054 | retrieveFDQuote - FD Decimal point issue | gkcharkravarthi | Closed | SL2-Moderate | gkcharkravarthi | 2015-06-09 | IP
3120 | administerFutureDatedFundTransfer - Update_Prepone_End_date_series_not_started | gkcharkravarthi | Closed | SL1-Severe | gkcharkravarthi | 2015-06-10 | IP
3203 | administerFutureDatedFundTransfer - RecurrCount_Increase | gkcharkravarthi | Closed | SL2-Moderate | gkcharkravarthi | 2015-06-12 | IP
3204 | administerFutureDatedFundTransfer - Update_Start_date_series_started - The record is modified and is getting cancelled/ DELETED. | gkcharkravarthi | Closed | SL1-Severe | gkcharkravarthi | 2015-06-12 | IP
3205 | Update_Postpone_End_date_series_not_started - UPDATE_DATE is null - READ_ONLY Field is null | gkcharkravarthi | Closed | SL2-Moderate | gkcharkravarthi | 2015-06-12 | IP
3220 | createFDAccount with nominee as major giving the finacle error message | gkcharkravarthi | Closed | SL2-Moderate | gkcharkravarthi | 2015-06-12 | IP
3227 | retriveFDQuote - giving the error message | gkcharkravarthi | Closed | SL2-Moderate | gkcharkravarthi | 2015-06-12 | IP
3259 | requestCardActivation - OverseasActivation/Deactivation | gkcharkravarthi | Closed | SL2-Moderate | gkcharkravarthi | 2015-06-13 | IP
3260 | requestCardActivation _DB_Verify_OverseasActivation_InvalidCardNumber_N - Error code is nor correct | gkcharkravarthi | Closed | SL2-Moderate | gkcharkravarthi | 2015-06-13 | IP
3276 | CustomerEventHistory_v1_0 - notifyEvent - notifyAction "LoginFailed" - does not creates record in Event_Details table | gkcharkravarthi | Closed | SL2-Moderate | pradeepmishrap | 2015-06-13 | IP
3510 | DepositeAccount - RetrieveFDTransactionHistory - throwing error when date filters are removed | pradeepmishrap | Closed | SL2-Moderate | pradeepmishrap | 2015-06-17 | IP
3519 | SIT1.1 - retrieveCardDetails - For blocked physical Card , retrieveCardDetails is not working. | nehapatpatia | Closed | SL2-Moderate | roxdsouza | 2015-06-17 | IP
3551 | PartyDataManagement_v1_1 - terminateFTPayee - JDBC error is thrown stating 'IPSSG01U.QUERY_FUTUREDATES' must be declared | pradeepmishrap | Closed | SL1-Severe | gkcharkravarthi | 2015-06-18 | IP
3575 | evaluateDepositAccountClosureEligibility - Error when trying to call this service when the user is having both the Savings and FD Account | gkcharkravarthi | Closed | SL2-Moderate | gkcharkravarthi | 2015-06-18 | IP
3941 | requestNetWorthStatement: BWENGINE error thrown | roxdsouza | Closed | SL2-Moderate | roxdsouza | 2015-06-25 | IP
3942 | evaluatePartyDocument: The error generated does not have a header | roxdsouza | Assigned | SL3-Minimal | roxdsouza | 2015-06-25 | IP
4214 | SIT1.1 -Finacle - Interbank fundtransfer Batch processing - Finacle is not able to process the fund transfer batch file for Interbank transactions | nehapatpatia | SIT Ready | SL2-Moderate | nehapatpatia | 2015-07-01 | IP