## Template
Test Execution Daily Status Report | [9 empty] | RED | Not Started
PROJECT DETAILS | [9 empty] | AMBER | In progress
Project Name: | Digital Banking | [8 empty] | GREEN | Completed
Team Name: | Ferrai
Sprint Number: | 4
Overall Status | Amber
Sprint Start Date: | 2014-07-15 | [9 empty] | On Hold
Sprint End Date: | 2014-08-06 | [9 empty] | Out-of-Scope
Remarks: | Project status is GREEN signifying that Sprint 4 stories will be delievered on time from testing perspective to date. Defects raised during Sprint 4 were fixed and retested
What was done today? | 1. Defects raised during sprint were fixed and Retested. 2. Performance issue with CreateAccount was highlighted.
What is the plan for tomorrow? | 1. Defects raised during sprint were fixed and Retested. 2. Performance issue with CreateAccount was highlighted.
Any risks / issues that need to be addressed immediately? | None
EXECUTION STATUS
Story Number | Story Name | Testing Start Date | Testing End Date | Total Test Cases | Test Cases executed | Test Cases Passed | Test Cases Failed | Status | Comments
37 | As a channel I want to be able to request statement for a given period | 2014-07-04 | 2014-07-09 | 17 | 17
DEFECT SUMMARY
Severity | New | Open | Fixed | Retest | Closed | Total | Comments
Severe (1) | 1 | 0 | 0 | 0 | 0 | 1
High (2) | 1 | 0 | 0 | 0 | 1 | 2
Medium (3) | 2 | 0 | 0 | 0 | 2 | 4
Low (4) | 2 | 0 | 0 | 0 | 0 | 2
GRAND TOTAL | 6 | 0 | 0 | 0 | 3 | 9
LIST OF OPEN DEFECTS (Only severe and high priority defects are mentioned here.)
Defect ID | Defect Description |  | Severity | Rasied On | Status | Assigned To | Comments
<Defect ID> | Defect Description |  | <Severity>
<Defect ID> | Defect Description |  | <Severity>
DOWNTIME TRACKER
Date | Comments | [5 empty] | No. of hours lost
<Date>

## Sheet2
Defect Metrics
Defect Severity | Outstanding | Fixed | Retest | Closed & Others | Total
SL1-Severe | 0 | 0 | 0 | 1 | 1
SL2-Moderate | 0 | 0 | 0 | 1 | 1
SL3-Minimal | 3 | 0 | 0 | 2 | 5
SL4-No Impact | 0 | 0 | 0 | 2 | 2
Grand Total | 3 | 0 | 0 | 6 | 9